## Build Plan
AI Interior Makeover: capabilities and build estimate
Stack: Bolt (front end), Supabase (backend), AI image-editing API. Edit blue cells (tokens, hours); totals update.
# | Capability | Priority | Approach | Tools | Build tokens (approx.) | Time (hours) | Tokens low | Tokens high | Labour cost (₹)
1 | Sign-up and login | MVP | Email and Google sign-in; row-level security so each user sees only their own rooms and designs | Bolt, Supabase Auth | 25000 | 1 | 15000 | 35000 | 600
2 | Room photo upload | MVP | Drag-and-drop upload, JPG/PNG up to 10 MB, client-side resize before upload, stored per user | Bolt, Supabase Storage | 30000 | 1.5 | 18000 | 42000 | 900
3 | Style selection | MVP | Style picker (Modern, Scandinavian, Japandi, Boho, Industrial, Traditional Indian) backed by a table of prompt templates | Bolt, Supabase Postgres | 20000 | 1 | 12000 | 28000 | 600
4 | AI makeover generation | MVP | Edge Function sends the photo plus the style prompt to the image-editing API and returns 2-3 variants; the API key stays server-side | Supabase Edge Functions, OpenAI image edit API (or similar) | 80000 | 4 | 48000 | 112000 | 2400
5 | Progress, errors and usage limits | MVP | Loading state with style previews, retry on failure, daily generation quota per user to control cost | Bolt, Supabase tables and Edge Function | 30000 | 2 | 18000 | 42000 | 1200
6 | Before/after slider | MVP | Draggable overlay comparing the original with the chosen concept | Bolt (React component) | 25000 | 1.5 | 15000 | 35000 | 900
7 | Personal gallery | MVP | Save, rename, favourite and delete designs; thumbnails loaded from storage | Bolt, Supabase Postgres and Storage | 40000 | 2 | 24000 | 56000 | 1200
8 | Share link and family vote | Differentiator | Public read-only page per design with a vote button; votes stored per concept | Bolt, Supabase Postgres | 45000 | 2.5 | 27000 | 63000 | 1500
9 | Budget Mode | Differentiator | User enters a budget in ₹; the text model returns structured JSON of changes with estimated costs that fit the budget | OpenAI API (structured output), Edge Function | 50000 | 3 | 30000 | 70000 | 1800
10 | Shop the Look | Differentiator | Each suggested item gets a search link to a retailer, built from the item name; no scraping | OpenAI API, Bolt | 35000 | 2 | 21000 | 49000 | 1200
11 | Vastu overlay | Differentiator | Vision model reads the photo and returns layout suggestions as short notes; shown beside the concept | OpenAI vision API, Edge Function | 40000 | 2 | 24000 | 56000 | 1200
12 | Landing page and demo gallery | Polish | Hero section, pre-generated sample makeovers for the demo, responsive layout | Bolt | 40000 | 2.5 | 24000 | 56000 | 1500
13 | Testing, deploy and demo rehearsal | Polish | Fix bugs, test on phone, deploy, rehearse the live reveal with a fallback gallery | Bolt hosting or Netlify, Supabase dashboard | 50000 | 3 | 30000 | 70000 | 1800
Summary by priority
| Priority | Capabilities |  |  | Build tokens | Time (hours) | Tokens low | Tokens high | Labour cost (₹)
| MVP | 7 |  |  | 250000 | 13 | 150000 | 350000 | 7800
| Differentiator | 4 |  |  | 170000 | 9.5 | 102000 | 238000 | 5700
| Polish | 2 |  |  | 90000 | 5.5 | 54000 | 126000 | 3300
| Total | 13 |  |  | 510000 | 28 | 306000 | 714000 | 16800
| Total working days (1 developer) |  |  |  |  | 3.5
| Time with parallel developers (hours) |  |  |  |  | 23.25
| Cash cost: tools and AI API (₹) |  |  |  |  | 6147.02
| Total cost of implementation incl. labour (₹) |  |  |  |  | 22947.02

## Assumptions
Assumptions (edit the blue cells)
Token estimate margin (±) | 40% | Build-token counts are rough; low/high columns apply this margin.
Developers working in parallel | 2 | Used for the parallel time estimate.
Hours per working day | 8 | Used to convert hours to days.
Notes
Tokens are build tokens only: prompts to Bolt, generated code and debugging rounds. Source: Claude's estimate, not measured.
Time is working hours for one person. Source: Claude's estimate.
Parallel estimate assumes only Differentiators (8-11) can be split across developers; MVP and Polish stay sequential.
Running cost per generation is separate: one image-edit call plus about 2,000-3,000 text tokens when Budget Mode and Vastu are on. Check the image API's current price before the demo.
Cut order if time runs short: drop 11, then 10, then 8; keep 9 only if the budget pitch is central.

## Cost
Cost of implementing AI Interior Makeover
Edit the blue cells; every cost below recalculates. Rates are assumptions or published prices as of Oct 2026 and can change.
Inputs
USD to INR rate | 88 | Assumption. Check the current rate.
Developer hourly rate (₹) | 600 | Placeholder. Set to your own rate, or 0 if your own time is free.
Bolt Pro plan (USD per month) | 25 | Bolt Pro: $25/month for 10M tokens, no daily cap. Free plan: 1M tokens/month with a 300K daily cap. Source: jetadmin.io Bolt pricing guide (Jul 2026).
Bolt Pro months needed | 1 | The full build (about 510K tokens, up to 714K) fits within one month of Pro.
Supabase Pro (USD per month) | 25 | Supabase Pro: $25/month. Free plan: 1 GB file storage, 500 MB database. Source: jetadmin.io Supabase pricing guide (Jul 2026).
Supabase Pro months needed | 1 | Set to 0 to stay on the Free plan; room photos and designs fill 1 GB quickly.
Image output tokens per image (medium, 1024x1024) | 439 | GPT Image 2.5 Sunburst: low 196, medium 439, high 1,756 tokens. Source: docs.kanaries.net (cites OpenAI's estimator).
Image output price (USD per 1M tokens) | 30 | OpenAI standard rate; $15 with Batch. Source: developers.openai.com/api/docs/models/gpt-image-2.5-sunburst.
Room photo input tokens per call | 1000 | Assumption. OpenAI has not published this for 2.5; read the usage field from real calls.
Image input price (USD per 1M tokens) | 8 | OpenAI rate for GPT Image 2.5 Sunburst.
Prompt tokens per call | 60 | Kanaries estimate for a short prompt.
Text input price (USD per 1M tokens) | 5 | OpenAI rate for GPT Image 2.5 Sunburst.
Images per generation (variants shown) | 3 | Capability 4 returns 2-3 variants.
Test generations during the build | 150 | Assumption.
Demo and judging generations | 100 | Assumption.
Text-model tokens per generation (Budget Mode, Vastu) | 3000 | Assumption: 2,000-3,000 tokens when both features are on.
Text-model price (USD per 1M tokens) | 5 | Assumption: uses the $5 text rate above. Your chosen model may differ.
Derived rates
Cost per image (USD) | 0.02147
Text cost per generation (USD) | 0.015
Cost per generation (₹) | 6.9881
Cost per 1,000 generations (₹) | 6988.08
Cost breakdown
Category | Item | Quantity | Unit cost (₹) | Cost (₹) | Basis
Tools | Bolt Pro subscription (months) | 1 | 2200 | 2200 | Plan price x months
Tools | Supabase Pro (months) | 1 | 2200 | 2200 | Plan price x months
Tools | Hosting (Bolt hosting or Netlify free tier) | 1 | 0 | 0 | Free tier assumed
AI API | Test generations during the build | 150 | 6.9881 | 1048.212 | Cost per generation x count
AI API | Demo and judging generations | 100 | 6.9881 | 698.808 | Cost per generation x count
Labour | Development hours (from Build Plan) | 28 | 600 | 16800 | Total hours x hourly rate
Cash cost: tools and AI API |  |  |  | 6147.02
Labour cost |  |  |  | 16800
Total cost of implementation |  |  |  | 22947.02
Cash cost if Bolt and Supabase stay on free tiers |  |  |  | 1747.02
Notes
gpt-image-1 was retired on Oct 23, 2026; the estimate uses its replacement, GPT Image 2.5 Sunburst, which supports image edits.
OpenAI publishes no edit-specific per-image price for 2.5, so image cost is output tokens plus an assumed reference-photo input. Log usage on real calls to confirm.
Costs exclude GST, payment fees and any custom domain. Bolt build tokens (about 510K) are covered by the plan price and not billed separately.
Running cost after launch is the cost per generation (B25), multiplied by your expected usage.